February 2023 Lebanese Armed Forces – Air Force (LAF-AF) Virtual Program Management Review (PMR) Meeting Minutes 28 February & 1 March 2023

-DAY 1-

Introductions

Mr. Lou Dockery opened the Virtual PMR welcoming all participants to the PMR, thanking everyone for their time and effort leading up to this point.

Program Status – Lou Dockery

Manpower: Mr. Dockery introduced the new members to the team, including the new WINI section chief Ms. Vaunceia Solano.

Program Accomplishments: Mr. Dockery began by discussing the program accomplishments, to include status of Mission Processing Unit (MPU), status of LOAs for aircraft 404 and 403, and repair items for aircraft 402.

Mission Processing Unit (MPU) Status: Mr. Dockery laid out the USAF’s next steps for the MPU software upgrade.  These include a Branch Oversight Board approval, formal Request for Proposal from Northrup Grumman Defense Systems (NGDS), Configuration Control Board approval, and finally contract award.  He gave a projected date for the software upgrade to be complete as NLT August 2023.

Contracting Status – Meagan Wooten

Modification Awarded:  Ms. Wooten stated she planned to award option year period 2, which will expire on 30 June 2024.  She will be starting the process with the Integrated Program Team (IPT) for follow-on sustainment effort.  She ended her brief by discussing the effort taken to correct the shipping issues due to Defense Contract Management Administration (DCMA) procedures.

Logistics Status – Bradley Dennis

Logistics – On Our Radar: Mr. Dennis discussed the different logistic tasks that would be coming up, such as the remaining items for the 402 engine repair and the 401/402 seat cushion replacement.

DISCLAIMER: “United States Government information is furnished to the Lebanese Armed Forces upon the condition that this information will not be released to another nation without specific authority of the Department of the Air Force of the United States; that individual or corporate rights originating the information will be provided substantially the same degree of security afforded it by the Department of Defense of the United States.”

Controlled by: USAF

Controlled by: AFLCMC/WINI

CUI Category: PROCURE, Operations Security Information

Limited Distribution Control: FED Only, REL TO USA, LBN

POC: DOCKERY, LOUIS, AFLCMC/WINI SAPM (louis.dockery@us.af.mil)

Electronic Combat International Security Assistance Program (ECISAP) – Santiago Goins

LE-D-QAC Status: Mr. Santiago Goins began this portion of the meeting by providing a summary of the status of each line on LE-D-QAC.

AN/ALE-47 Update: Mr. Goins stated that ECISAP will deliver the Mission Date File (MDF) software update 9-12 months after contract order.  He added that should the LE-D-QAC Period of Performance (PoP) extension be delayed at all; this delivery will be delayed.

Missile Warning System: ECISAP discussed the engineering analysis briefing covering the AN/AAR-47, AN/AAR-57, and AAR-60, which had been provided prior to this PMR.  They stated that the AN/AAR-57 and AAR-60 Study which has been undertaken to help determine which system will function the best in Lebanon is projected to be complete in July 2023.

Potential LOA PoP Lapse: ECISAP mentioned that they were working with AFSAC to extend the PoP on LE-D-QAC to avoid a break in service.  WINI leadership voiced their commitment to support this effort from their end.

New Action Item PMRFEB2023-1: ECISAP PoP Extension Support

Northrop Grumman Defense Systems (NGDS) – Calvin O’Reilly

Top Open Actions:  Mr. Calvin O’Reilly asked the LAF if they had shipped the old engine from out of AC-402 yet, when they answered that they had not he explained that the longer that they wait the greater the risk of more damage to that old engine.  Mr. O’Reilly also stated that the 3 requested fuel system components needed to repair AC-402 were ready to ship and that they should receive authorization to ship in the week following the PMR.

New Action Item PMRFEB2023-8: 402 Engine Return

Shipment Status:  Mr. O’Reilly provided an up-to-date list of shipments.

Obsolescence:  Leading into the obsolescence discussion Mr. Lou Dockery asked the LAF what their plans for obsolescence upgrading were, to which the LAF replied that they currently have no plans to upgrade either AC-401 or AC-402 and that both planes would be simply used as training planes in the future.  For their information, Mr. Luis Cuellar, an engineer from NGDS, briefed them on the current obsolescence issues that they are facing in their fleet.  They recommended that they upgrade the L3/Harris MX-15D EO/IR System (Two Box) and associated MMFCS components, the MPS Heli-Coder II Date Link System, the L3/Harris RF-5800 Man-Pack Radio System, the AN/AAR-60 Hybrid MLDS MWS, the NGDS MMFCS GEN2 MPU, and the MMFCS Analog/NTSC Video Architecture and associated components for the AC-401.  They also recommended that they upgrade the L3/Harris MX-15DiA EO/IR System and associated components, the BMS Heli-Coder II (HC2) Data Link System, the L3/Harris RF-5800 Man-pack Radio System, the NGDS MMFCS GEN2 MPU, the Analog/NTSC Video Architecture and associated components, and the AN/AAR-60 Hybrid MLDS MWS for the AC-402.

Repair Return/Calibrations: Mr. O’Reilly stated that the Pitot Tester, IFR 6000, and NAV COM Test Set were all calibrated and that the ALE 47 was calibrated and will be shipped back pending DMCA approval.

LAF 402: Mr. O’Reilly provided a troubleshooting report and timeline for the AC-402 Engine Overheat.    -END OF DAY 1-

-DAY 2-

Action Items Review:

- PMRAUG2017-19 –This action item to remain open while USG investigates FDS.

- PMRAUG2018-4 – Ms. Mary Kelly stated that the stock number provided was an older stock number and not correct.  She asked if the LAF-AF had any AEAs to which they replied that they did not.  Ms. Kelly will investigate this issue further.  Action item will remain open until received.

- PREPMRAUG19-7 – Action item is currently on hold.

- PREPMRAUG19-13 – Mr. Dockery suggested that this action item be closed, LAF agreed.  Action item to be closed.

- PMRMAR20-5 – Action item ongoing.

- PMRFEB2018-14 – Action item to be closed.

- PREPMRAUG19-3 – LAF suggests action item can be removed since it has been tied into the LOA for the 4th aircraft.  Action item to be removed pending system improvements of current systems.

- PMRAPR2021-6 – Information was provided to the ODC to follow up on this.  LAF requests information sent again.  Action item will remain open until information is again sent to ODC.

- PMRDEC2021-2 – Action item to be closed due to new action item taken [PMRFEB2023-2].

- PMRSEPT2022-1 – Action item ongoing.

- PMRSEPT2022-2 – Action item to be closed.

- PMRSEPT2022-3 – Action item to be closed due to new action item taken [PMRFEB2023-2].

New Action Items review

- PMRFEB2023-1 – ECISAP LE-D-QAC PoP Extension Support.  AFSAC currently looking into funding options, WINI to support.

- PMRFEB2023-2 – MWS Troubleshooting.  WINI to request pricing from NGDS for field evaluation.

- PMRFEB2023-3 – Obsolescence Plan.  WINI working to send NGDS obsolescence brief along with WINI obsolescence plan.

- PMRFEB2023-4 – Historic MWS Test Data.  WINI working to get data from NGDS.

- PMRFEB2023-5 – CLS Extension.  AFSAC to request LOR from LAF.

- PMRFEB2023-6 – CLS Expansion.  WINI to request P&A from NGDS.

- PMRFEB2023-7 – HEA R&R.  Army and LAF coordinating on pickup.

- PMRFEB2023-8 – 402 Engine Return.  NGDS requested return of damaged engine from 402 for evaluation.

AFSAC – Mary Kelly

LOA Schedule – New AC-208 and L-403 Upgrade: Ms. Mary Kelly brief on the current status and projected LOA schedule for the L-404 purchase and L-403 upgrade.

Financial Status – Kristin Draper

Current Financial Status: Ms. Kristin Draper went over the finance chart and explained how there was a realignment, but no new funds were needed.

Lebanon Hellfire – Marc Nixon

Mr. Kyle Perkins, USASAC Country Program Manager introduced Mr. Marc Nixon who replaced Mr. Josh Stinson for the AMCOM HELLFIRE Program. Colonel Saifi welcomed Mr. Nixon to the Program. Mr. Nixon provided a line-by-line overview of cases LE-B-WFB, LE-B-WFC, LE-B-WFO, U7-B-UZA and Open Action Items.

Items that generated additional discussion were as follows:

LE-B-WFB & PMR April 2021 Action Item #002 - The Lebanese Air Force was advised by Tactical Aviation and Ground Munitions (TAGMS), that in country conversion efforts to convert HELLFIRE missiles to version R-3 under FMS case LE-B-WFB are scheduled for the September – October 2023 timeframe and would require two weeks to complete. The LAF advised that anytime in October 2023 timeframe would be acceptable for the LAF and that the missiles needing conversion are at two locations at this time.  However, they will all be moved to 1 central location for conversion.  Action item can be closed at this time.

Regarding the 80 each AGM-114R missiles for case LE-B-WFO, the LAF requested information regarding conversion services for the impending HELLFIRE missile delivery scheduled for September 2023. Per TAGM International, the 80 each missiles will come off the production line as version R-3 missiles.

Stockpile Reliability Report – TAGM advised the report should be completed no later than 30 April 2023. Per the LAF request, SAMD will arrange a meeting with country and TAGM in May 2023 to discuss the results.

HELLFIRE Electronic Assembly (HEA) Repair & Return (R&R) – USASAC inquired if the HEA had been returned to the Lebanese Freight Forwarder from Northrup Grumman and if the LAF has submitted formal repair request to USASAC-NC on case LE-B-WFB/Line 029. Action item PMRFEB2023-7 was created.

The LAF thanked all participants for their continued support and indicated the importance of this Program to the Lebanese Air Force.

--ACTION ITEM PMRFEB2023-7

DESCRIPTION: Repair & Return of HELLFIRE Electronics Assembly Shipped to Northrup Grumman.

DATE OF REQUEST: 3/1/23

Desired outcome: The LAF will submit repair and return request to USASAC-NC under FMS Case LE-B-WFB. The LAF will query its Freight Forwarder to pick up HELLFIRE Electronics Assembly at Northrup Grumman and hold until disposition instructions are provided by USASAC-NC.

ACTIONEE: LAF

Suspense Date: 4/3/23.

-END OF DAY 2-

| COL PSC Pilot Michel Saifi Commander, Lebanese Armed Forces | Maj Helen Marino Country Director, SAF/IA |
| --- | --- |
| Ms. Mary Kelly Command Country Manager, AFSAC | Mr. John Perkins Country Program Manager U.S. Army Security Assistance Command |
| Mr. Louis Dockery Security Assistance Program Manager ADLCMC/WINI |  |